## Gantt
Boards - Battle Nations (by days)
[5 empty] | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026
| Start | End | % Complete | Notes | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Battle Nations |  |  | 100% |  | 17: Battle Nations
Initial Project Description | 17-Feb-2026 | 20-Feb-2026 | 100% |  | 17: Initial Project Description (17-Feb-26 - 20-Feb-26); 18: Project Description (17-Feb-26 - 20-Feb-26); 19: Project Description (17-Feb-26 - 20-Feb-26); 20: Project Description (17-Feb-26 - 20-Feb-26)
Build Initial Gannt chart | 2026-02-20 | 27-Feb-2026 | 100% |  | 20: Finish Gant chart (20-Feb-26 - 27-Feb-26)
Initial Vision Statement | 20-Feb-2026 | 2026-03-27 | 100% |  | 20: Initial Vision Statement (20-Feb-26 - 27-Feb-26)
Build UML For all classes and Interfaces | 2026-02-27 | 07-Mar-2026 | 100% |  | 26: Build UML For all classes We have created (27-Feb-26 - 07-Mar-26)
Code Player class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Code Player class (25-Feb-26 - 27-Feb-26); 26: Code Player class (25-Feb-26 - 27-Feb-26); 27: Code Player class (25-Feb-26 - 27-Feb-26)
Javadocs for Player Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Javadocs for Player Class (25-Feb-26 - 27-Feb-26); 26: Javadocs for Player Class (25-Feb-26 - 27-Feb-26); 27: Javadocs for Player Class (25-Feb-26 - 27-Feb-26)
Code Territory Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Code Territory Class (25-Feb-26 - 27-Feb-26); 26: Code Territory Class (25-Feb-26 - 27-Feb-26); 27: Code Territory Class (25-Feb-26 - 27-Feb-26)
Write Test Code for Territory Class | 25-Feb-2026 | 27-Feb-2026 | 0% | Now is Late: Must get finished by 3/8/2025 | 25: Write Test Code for Territory Class (25-Feb-26 - 27-Feb-26); 26: Write Test Code for Territory Class (25-Feb-26 - 27-Feb-26); 27: Write Test Code for Territory Class (25-Feb-26 - 27-Feb-26)
Javadocs for Territory Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Javadocs for Territory Class (25-Feb-26 - 27-Feb-26); 26: Javadocs for Territory Class (25-Feb-26 - 27-Feb-26); 27: Javadocs for Territory Class (25-Feb-26 - 27-Feb-26)
Code Region Class | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 25: Code Region Class (25-Feb-26 - 27-Feb-26); 26: Code Region Class (25-Feb-26 - 27-Feb-26); 27: Code Region Class (25-Feb-26 - 27-Feb-26)
Javadocs for Region Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Javadocs for Region Class (25-Feb-26 - 27-Feb-26); 26: Javadocs for Region Class (25-Feb-26 - 27-Feb-26); 27: Javadocs for Region Class (25-Feb-26 - 27-Feb-26)
Write Test Code for Region Class | 27-Feb-2026 | 06-Mar-2026 | 71.43% | 5 out of 7 methods are properly tested | 27: Write Test Code for Region Class (27-Feb-26 - 06-Feb-26)
Code Map Class | 27-Feb-2026 | 06-Mar-2026 | 0%
Javadocs for Map Class | 27-Feb-2026 | 06-Mar-2026 | 0% |  | 27: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 28: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 1: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 2: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 3: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 4: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 5: Javadocs for Map Class (27-Feb-26 - 06-Mar-26); 6: Javadocs for Map Class (27-Feb-26 - 06-Mar-26)
Create Loading Screen | 27-Feb-2026 | 06-Mar-2026 | 0% |  | 27: Create Loading Screen (27-Feb-26 - 06-Mar-26); 28: Create Loading Screen (27-Feb-26 - 06-Mar-26); 1: Create Loading Screen (27-Feb-26 - 06-Mar-26); 2: Create Loading Screen (27-Feb-26 - 06-Mar-26); 3: Create Loading Screen (27-Feb-26 - 06-Mar-26); 4: Create Loading Screen (27-Feb-26 - 06-Mar-26); 5: Create Loading Screen (27-Feb-26 - 06-Mar-26); 6: Create Loading Screen (27-Feb-26 - 06-Mar-26)
Create Main Screen for choosing game mode | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Create Start Screen (27-Feb-26 - 06-Mar-26); 28: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 1: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 2: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 3: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 4: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 5: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 6: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26)
Create Settings Screen for game | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 28: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 1: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 2: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 3: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 4: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 5: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 6: Create Settings Screen for game (27-Feb-26 - 06-Mar-26)
Start Main controller for displaying Different screens | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 28: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 1: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 2: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 3: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 4: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 5: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 6: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26)
Update TerritoryType Enum | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Update TerritoryType Enum (27-Feb-26 - 06-Mar-26)
Build out first map logic | 27-Feb-2026 | 06-Mar-2026 | 0% | Max had roadblock in other class, couldn’t get to this | 27: Build out first map logic (27-Feb-26 - 06-Mar-26); 28: Build out first map logic (27-Feb-26 - 06-Mar-26); 1: Build out first map logic (27-Feb-26 - 06-Mar-26); 2: Build out first map logic (27-Feb-26 - 06-Mar-26); 3: Build out first map logic (27-Feb-26 - 06-Mar-26); 4: Build out first map logic (27-Feb-26 - 06-Mar-26); 5: Build out first map logic (27-Feb-26 - 06-Mar-26); 6: Build out first map logic (27-Feb-26 - 06-Mar-26)
Build Flow Chart | 2026-02-18 | 04-Mar-2026 | 100% |  | 28: Build Flow Chart (19-Feb-26 - 04-Mar-26)
Start game flow logic and wire map to update | 02-Mar-2026 | 13-Mar-2026 |  |  | 2: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 3: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 4: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 5: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 6: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 7: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 8: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 9: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 10: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 11: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 12: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 13: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26)
Start Building User Manual | 06-Mar-2026 | 13-Mar-2026 |  |  | 6: Start Building User Manual (06-Mar-26 - 13-Mar-26); 7: Start Building User Manual (06-Mar-26 - 13-Mar-26); 8: Start Building User Manual (06-Mar-26 - 13-Mar-26); 9: Start Building User Manual (06-Mar-26 - 13-Mar-26); 10: Start Building User Manual (06-Mar-26 - 13-Mar-26); 11: Start Building User Manual (06-Mar-26 - 13-Mar-26); 12: Start Building User Manual (06-Mar-26 - 13-Mar-26); 13: Start Building User Manual (06-Mar-26 - 13-Mar-26)
Test Code for player's troop multiplies | 06-Mar-2026 | 13-Mar-2026 |  |  | 6: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 7: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 8: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 9: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 10: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 11: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 12: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26); 13: Test Code for player's troop multiplies (06-Mar-26 - 13-Mar-26)
Finalize logic for main screen and settings | 11-Mar-2026 | 18-Mar-2026 |  |  | 11: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 12: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 13: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 14: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 15: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 16: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 17: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26); 18: Finalize logic for main screen and settings (11-Mar-26 - 18-Mar-26)
Get Basic game working | 12-Mar-2026 | 19-Mar-2026 |  |  | 12: Get Basic game working (12-Mar-26 - 19-Mar-26); 13: Get Basic game working (12-Mar-26 - 19-Mar-26); 14: Get Basic game working (12-Mar-26 - 19-Mar-26); 15: Get Basic game working (12-Mar-26 - 19-Mar-26); 16: Get Basic game working (12-Mar-26 - 19-Mar-26); 17: Get Basic game working (12-Mar-26 - 19-Mar-26); 18: Get Basic game working (12-Mar-26 - 19-Mar-26); 19: Get Basic game working (12-Mar-26 - 19-Mar-26)
Continue work on user manual | 14-Mar-2026 | 11-Apr-2026 |  |  | 14: Continue work on user manual (14-Mar-26 - 11-Apr-26); 15: Continue work on user manual (14-Mar-26 - 11-Apr-26); 16: Continue work on user manual (14-Mar-26 - 11-Apr-26); 17: Continue work on user manual (14-Mar-26 - 11-Apr-26); 18: Continue work on user manual (14-Mar-26 - 11-Apr-26); 19: Continue work on user manual (14-Mar-26 - 11-Apr-26); 20: Continue work on user manual (14-Mar-26 - 11-Apr-26); 21: Continue work on user manual (14-Mar-26 - 11-Apr-26); 22: Continue work on user manual (14-Mar-26 - 11-Apr-26); 23: Continue work on user manual (14-Mar-26 - 11-Apr-26); 24: Continue work on user manual (14-Mar-26 - 11-Apr-26); 25: Continue work on user manual (14-Mar-26 - 11-Apr-26); 26: Continue work on user manual (14-Mar-26 - 11-Apr-26); 27: Continue work on user manual (14-Mar-26 - 11-Apr-26); 28: Continue work on user manual (14-Mar-26 - 11-Apr-26); 29: Continue work on user manual (14-Mar-26 - 11-Apr-26); 30: Continue work on user manual (14-Mar-26 - 11-Apr-26); 31: Continue work on user manual (14-Mar-26 - 11-Apr-26); 1: Continue work on user manual (14-Mar-26 - 11-Apr-26); 2: Continue work on user manual (14-Mar-26 - 11-Apr-26); 3: Continue work on user manual (14-Mar-26 - 11-Apr-26); 4: Continue work on user manual (14-Mar-26 - 11-Apr-26); 5: Continue work on user manual (14-Mar-26 - 11-Apr-26); 6: Continue work on user manual (14-Mar-26 - 11-Apr-26); 7: Continue work on user manual (14-Mar-26 - 11-Apr-26); 8: Continue work on user manual (14-Mar-26 - 11-Apr-26); 9: Continue work on user manual (14-Mar-26 - 11-Apr-26); 10: Continue work on user manual (14-Mar-26 - 11-Apr-26); 11: Continue work on user manual (14-Mar-26 - 11-Apr-26)
Add second and third game mode | 18-Mar-2026 | 25-Mar-2026 |  |  | 18: Add second and third game mode (18-Mar-26 - 25-Mar-26); 19: Add second and third game mode (18-Mar-26 - 25-Mar-26); 20: Add second and third game mode (18-Mar-26 - 25-Mar-26); 21: Add second and third game mode (18-Mar-26 - 25-Mar-26); 22: Add second and third game mode (18-Mar-26 - 25-Mar-26); 23: Add second and third game mode (18-Mar-26 - 25-Mar-26); 24: Add second and third game mode (18-Mar-26 - 25-Mar-26); 25: Add second and third game mode (18-Mar-26 - 25-Mar-26)
Write more test code where needed | 27-Mar-2026 | 03-Apr-2026 |  |  | 27: Write more test code where needed (27-Mar-26 - 03-Apr-26); 28: Write more test code where needed (27-Mar-26 - 03-Apr-26); 29: Write more test code where needed (27-Mar-26 - 03-Apr-26); 30: Write more test code where needed (27-Mar-26 - 03-Apr-26); 31: Write more test code where needed (27-Mar-26 - 03-Apr-26); 1: Write more test code where needed (27-Mar-26 - 03-Apr-26); 2: Write more test code where needed (27-Mar-26 - 03-Apr-26); 3: Write more test code where needed (27-Mar-26 - 03-Apr-26)
Polish Game + Visuals | 03-Apr-2026 | 17-Apr-2026 |  |  | 3: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 4: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 5: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 6: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 7: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 8: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 9: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 10: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 11: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 12: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 13: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 14: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 15: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 16: Polish Game + Visuals (03-Apr-26 - 17-Apr-26); 17: Polish Game + Visuals (03-Apr-26 - 17-Apr-26)
Add music to game | 03-Apr-2026 | 17-Apr-2026 |  |  | 3: Add music to game (03-Apr-26 - 17-Apr-26); 4: Add music to game (03-Apr-26 - 17-Apr-26); 5: Add music to game (03-Apr-26 - 17-Apr-26); 6: Add music to game (03-Apr-26 - 17-Apr-26); 7: Add music to game (03-Apr-26 - 17-Apr-26); 8: Add music to game (03-Apr-26 - 17-Apr-26); 9: Add music to game (03-Apr-26 - 17-Apr-26); 10: Add music to game (03-Apr-26 - 17-Apr-26); 11: Add music to game (03-Apr-26 - 17-Apr-26); 12: Add music to game (03-Apr-26 - 17-Apr-26); 13: Add music to game (03-Apr-26 - 17-Apr-26); 14: Add music to game (03-Apr-26 - 17-Apr-26); 15: Add music to game (03-Apr-26 - 17-Apr-26); 16: Add music to game (03-Apr-26 - 17-Apr-26); 17: Add music to game (03-Apr-26 - 17-Apr-26)
Create 2nd and 3rd map if there is time | 03-Apr-2026 | 17-Apr-2026 |  |  | 3: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 4: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 5: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 6: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 7: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 8: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 9: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 10: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 11: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 12: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 13: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 14: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 15: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 16: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26); 17: Create 2nd and 3rd map if there is time (03-Apr-26 - 17-Apr-26)
Finalize User manual | 03-Apr-2026 | 17-Apr-2026 |  |  | 3: Finalize User manual (03-Apr-26 - 17-Apr-26); 4: Finalize User manual (03-Apr-26 - 17-Apr-26); 5: Finalize User manual (03-Apr-26 - 17-Apr-26); 6: Finalize User manual (03-Apr-26 - 17-Apr-26); 7: Finalize User manual (03-Apr-26 - 17-Apr-26); 8: Finalize User manual (03-Apr-26 - 17-Apr-26); 9: Finalize User manual (03-Apr-26 - 17-Apr-26); 10: Finalize User manual (03-Apr-26 - 17-Apr-26); 11: Finalize User manual (03-Apr-26 - 17-Apr-26); 12: Finalize User manual (03-Apr-26 - 17-Apr-26); 13: Finalize User manual (03-Apr-26 - 17-Apr-26); 14: Finalize User manual (03-Apr-26 - 17-Apr-26); 15: Finalize User manual (03-Apr-26 - 17-Apr-26); 16: Finalize User manual (03-Apr-26 - 17-Apr-26); 17: Finalize User manual (03-Apr-26 - 17-Apr-26)
Finalize Project + Prepare for Customer Presentation | 07-Apr-2026 | 15-Apr-2026 |  |  | 7: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 8: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 9: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 10: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 11: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 12: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 13: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 14: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26); 15: Finalize Project + Prepare for Customer Presentation (07-Apr-26 - 15-Apr-26)
Update whatever requests we get from customer | 14-Apr-2026 | 24-Apr-2026 |  |  | 14: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 15: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 16: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 17: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 18: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 19: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 20: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 21: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 22: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 23: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26); 24: Update whatever requests we get from customer (14-Apr-26 - 24-Apr-26)
Finalize all Semester requirements | 14-Apr-2026 | 24-Apr-2026 |  |  | 14: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 15: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 16: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 17: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 18: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 19: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 20: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 21: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 22: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 23: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26); 24: Finalize all Semester requirements (14-Apr-26 - 24-Apr-26)