## Gantt
Boards - Battle Nations (by days)
[5 empty] | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Feb-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Mar-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | Apr-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026 | May-2026
| Start | End | % Complete | Notes | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Battle Nations |  |  | 100% |  | 17: Battle Nations
Initial Project Description | 17-Feb-2026 | 20-Feb-2026 | 100% |  | 17: Initial Project Description (17-Feb-26 - 20-Feb-26); 18: Project Description (17-Feb-26 - 20-Feb-26); 19: Project Description (17-Feb-26 - 20-Feb-26); 20: Project Description (17-Feb-26 - 20-Feb-26)
Build Initial Gannt chart | 2026-02-20 | 27-Feb-2026 | 100% |  | 20: Finish Gant chart (20-Feb-26 - 27-Feb-26)
Initial Vision Statement | 20-Feb-2026 | 2026-03-27 | 100% |  | 20: Initial Vision Statement (20-Feb-26 - 27-Feb-26)
Code Player class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Code Player class (25-Feb-26 - 27-Feb-26); 26: Code Player class (25-Feb-26 - 27-Feb-26); 27: Code Player class (25-Feb-26 - 27-Feb-26)
Javadocs for Player Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Javadocs for Player Class (25-Feb-26 - 27-Feb-26); 26: Javadocs for Player Class (25-Feb-26 - 27-Feb-26); 27: Javadocs for Player Class (25-Feb-26 - 27-Feb-26)
Code Territory Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Code Territory Class (25-Feb-26 - 27-Feb-26); 26: Code Territory Class (25-Feb-26 - 27-Feb-26); 27: Code Territory Class (25-Feb-26 - 27-Feb-26)
Javadocs for Territory Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Javadocs for Territory Class (25-Feb-26 - 27-Feb-26); 26: Javadocs for Territory Class (25-Feb-26 - 27-Feb-26); 27: Javadocs for Territory Class (25-Feb-26 - 27-Feb-26)
Code Region Class | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 25: Code Region Class (25-Feb-26 - 27-Feb-26); 26: Code Region Class (25-Feb-26 - 27-Feb-26); 27: Code Region Class (25-Feb-26 - 27-Feb-26)
Javadocs for Region Class | 25-Feb-2026 | 27-Feb-2026 | 100% |  | 25: Javadocs for Region Class (25-Feb-26 - 27-Feb-26); 26: Javadocs for Region Class (25-Feb-26 - 27-Feb-26); 27: Javadocs for Region Class (25-Feb-26 - 27-Feb-26)
Write Test Code for Region Class | 27-Feb-2026 | 06-Mar-2026 | 100% | 5 out of 7 methods are properly tested | 27: Write Test Code for Region Class (27-Feb-26 - 06-Feb-26)
Create Start Screen | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Create Start Screen (27-Feb-26 - 06-Mar-26); 28: Create Loading Screen (27-Feb-26 - 06-Mar-26); 1: Create Loading Screen (27-Feb-26 - 06-Mar-26); 2: Create Loading Screen (27-Feb-26 - 06-Mar-26); 3: Create Loading Screen (27-Feb-26 - 06-Mar-26); 4: Create Loading Screen (27-Feb-26 - 06-Mar-26); 5: Create Loading Screen (27-Feb-26 - 06-Mar-26); 6: Create Loading Screen (27-Feb-26 - 06-Mar-26)
Create Main Screen for choosing game mode | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Create Start Screen (27-Feb-26 - 06-Mar-26); 28: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 1: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 2: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 3: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 4: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 5: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26); 6: Create Main Screen for choosing game mode (27-Feb-26 - 06-Mar-26)
Create Settings Screen for game | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 28: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 1: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 2: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 3: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 4: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 5: Create Settings Screen for game (27-Feb-26 - 06-Mar-26); 6: Create Settings Screen for game (27-Feb-26 - 06-Mar-26)
Start Main controller for displaying Different screens | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 28: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 1: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 2: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 3: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 4: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 5: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26); 6: Start Main controller for displaying Different screens (27-Feb-26 - 06-Mar-26)
Build UML For all classes and Interfaces | 2026-02-27 | 2026-03-06 | 100% |  | 27: Build UML For all classes We have created (27-Feb-26 - 07-Mar-26)
Update TerritoryType Enum | 27-Feb-2026 | 06-Mar-2026 | 100% |  | 27: Update TerritoryType Enum (27-Feb-26 - 06-Mar-26)
Build out first map logic | 27-Feb-2026 | 06-Mar-2026 | 100% | Max had roadblock in other class, couldn’t get to this | 27: Build out first map logic (27-Feb-26 - 06-Mar-26); 28: Build out first map logic (27-Feb-26 - 06-Mar-26); 1: Build out first map logic (27-Feb-26 - 06-Mar-26); 2: Build out first map logic (27-Feb-26 - 06-Mar-26); 3: Build out first map logic (27-Feb-26 - 06-Mar-26); 4: Build out first map logic (27-Feb-26 - 06-Mar-26); 5: Build out first map logic (27-Feb-26 - 06-Mar-26); 6: Build out first map logic (27-Feb-26 - 06-Mar-26)
Build Flow Chart | 2026-02-27 | 04-Mar-2026 | 100% |  | 28: Build Flow Chart (27-Feb-26 - 04-Mar-26)
Start game flow logic and wire map to update | 06-Mar-2026 | 2026-03-13 | 100% | Game flow logic is created in backend, but not used with any GUI. GUI Also cant update any territories yet | 2: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 3: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 4: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 5: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 6: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 7: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 8: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 9: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 10: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 11: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 12: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26); 13: Start game flow logic and wire map to update (02-Mar-26 - 13-Mar-26)
Code Map Class | 06-Mar-2026 | 13-Mar-2026 | 100% |  | 6: Code Map Claass (06-Mar-26-13-Mar-26)
Display First Map | 06-Mar-2026 | 13-Mar-2026 | 100% |  | 6: Display First Map (06-Mar-26-13-Mar-26)
Create Service Class for player's troop multiplies | 06-Mar-2026 | 13-Mar-2026 | 100% |  | 6: Create Service Class for player's troop multiplies (06-Mar-26-13-Mar-26)
Create Service Class for attacking | 06-Mar-2026 | 13-Mar-2026 | 100% |  | 13: Create Service Class for attacking (13-Mar-26-20-Mar-2026)
Create Service class for Fortifying | 13-Mar-2026 | 2026-03-20 | 100% |  | 13: Create Service Class for fortifying (13-Mar-26-20-Mar-2026)
Create GameLogic class | 13-Mar-2026 | 2026-03-20 | 100% |  | 13: Create GameLogic class (13-Mar-26-20-Mar-2026)
Create GUI Screen for getting player names | 13-Mar-2026 | 2026-03-20 | 100% |  | 13: Create GUI Screen for getting player names (13-Mar-26-20-Mar-2026)
Refactor file reading service for map | 13-Mar-2026 | 2026-03-20 | 100% |  | 13: Refactor file reading service for map (13-Mar-26-20-Mar-2026)
Allow users to click on territories displayed by map | 13-Mar-2026 | 2026-03-20 | 100% |  | 13: Allow users to click on territories displayed by map (13-Mar-26-20-Mar-2026)
Get Basic game working | 2026-03-20 | 2026-03-27 | 100% |  | 13: Get Basic game working (12-Mar-26 - 19-Mar-26); 14: Get Basic game working (12-Mar-26 - 19-Mar-26); 15: Get Basic game working (12-Mar-26 - 19-Mar-26); 16: Get Basic game working (12-Mar-26 - 19-Mar-26); 17: Get Basic game working (12-Mar-26 - 19-Mar-26); 18: Get Basic game working (12-Mar-26 - 19-Mar-26); 19: Get Basic game working (12-Mar-26 - 19-Mar-26); 22: Get Basic game working (20-Mar-26 - 27-Mar-26)
Add second and third game mode | 18-Mar-2026 | 25-Mar-2026 | 50% | Game Modes are Added, But not Implemented | 22: Add second and third game mode (20-Mar-26-27-Mar-26)
Write Test Code for Territory Class | 27-Mar-2026 | 03-Apr-2026 | 100% |  | 27: Write test code for Territory Class (27-Mar-26 - 03-Apr-26); 28: Write more test code where needed (27-Mar-26 - 03-Apr-26); 29: Write more test code where needed (27-Mar-26 - 03-Apr-26); 30: Write more test code where needed (27-Mar-26 - 03-Apr-26); 31: Write more test code where needed (27-Mar-26 - 03-Apr-26); 1: Write more test code where needed (27-Mar-26 - 03-Apr-26); 2: Write more test code where needed (27-Mar-26 - 03-Apr-26); 3: Write more test code where needed (27-Mar-26 - 03-Apr-26)
Implement Highlight Territory Logic | 27-Mar-2026 | 03-Apr-2026 | 100% |  | 27: Create Territory Highlighting Logic (27-Mar-26 - 03-Apr-26); 28: Write more test code where needed (27-Mar-26 - 03-Apr-26); 29: Write more test code where needed (27-Mar-26 - 03-Apr-26); 30: Write more test code where needed (27-Mar-26 - 03-Apr-26); 31: Write more test code where needed (27-Mar-26 - 03-Apr-26); 1: Write more test code where needed (27-Mar-26 - 03-Apr-26); 2: Write more test code where needed (27-Mar-26 - 03-Apr-26); 3: Write more test code where needed (27-Mar-26 - 03-Apr-26)
Create Region Display | 27-Mar-2026 | 03-Apr-2026 | 100% |  | 27: Create Regions Display (27-Mar-26 - 03-Apr-26); 28: Write more test code where needed (27-Mar-26 - 03-Apr-26); 29: Write more test code where needed (27-Mar-26 - 03-Apr-26); 30: Write more test code where needed (27-Mar-26 - 03-Apr-26); 31: Write more test code where needed (27-Mar-26 - 03-Apr-26); 1: Write more test code where needed (27-Mar-26 - 03-Apr-26); 2: Write more test code where needed (27-Mar-26 - 03-Apr-26); 3: Write more test code where needed (27-Mar-26 - 03-Apr-26)
Polish Game + Visuals | 2026-03-27 | 2026-04-03 | 35% |  | 27: Write Test Code for all Services (27-Mar-26 - 03-Apr-26); 28: Write more test code where needed (27-Mar-26 - 03-Apr-26); 29: Write more test code where needed (27-Mar-26 - 03-Apr-26); 30: Write more test code where needed (27-Mar-26 - 03-Apr-26); 31: Write more test code where needed (27-Mar-26 - 03-Apr-26); 1: Write more test code where needed (27-Mar-26 - 03-Apr-26); 2: Write more test code where needed (27-Mar-26 - 03-Apr-26); 3: Write more test code where needed (27-Mar-26 - 03-Apr-26)
Write Test Code for all Services | 2026-03-27 | 2026-04-03 | 0% |  | 5: Add music to game (03-Apr-26 - 10-Apr-26)
Add music to game | 2026-03-27 | 2026-04-03 | 50% |  | 3: Finalize All Code for battle Nations (03-Apr-26 - 10-Apr-26
Create 2nd and 3rd map if there is time | 03-Apr-2026 | 2026-04-10 | 100% | Max did this 3/20/2026 | 3: Create 2nd and 3rd map if there is time (03-Apr-26 - 10-Apr-26)
Finalize All Code for BattleNations | 2026-04-10 | 17-Apr-2026 |  |  | 10: Finalize Code For BattleNations (10-Apr-26 - 17-Apr-26)
Finalize User manual | 2026-04-10 | 17-Apr-2026 |  |  | 10: Finalize User manual (10-Apr-26 - 17-Apr-26)
Prepare for Customer Presentation | 2026-04-10 | 17-Apr-2026 |  |  | 10: Prepare For Final Presentation (10-Apr-26 - 17-Apr-26)
Update whatever requests we get from customer | 2026-04-17 | 24-Apr-2026 |  |  | 17: Update whatever requests we get from customer (17-Apr-26 - 24-Apr-26)
Finalize all Semester requirements | 2026-04-17 | 24-Apr-2026 |  |  | 17: Finalize all Semester requirements (17-Apr-26 - 24-Apr-26)